## Main
Today | Copy this doc and follow the link below for instructions. |  | 45 |  | 0 |  |  | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | This doc is modified from: http://bit.ly/IGDPD_BDC_Example
2017-12-05 | BurndownChartInstructions |  | Hours | Hours | Hours |  |  | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Tue | Tue | Tue | Tue | Tue
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-04 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | Detailed Information | #
Task Assignments
1 | Alter the Collider Between the Pug & Items (land on items) | S | 0.5 | 0.25 | 0 |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5
2 | Add new backgrounds (1 per level) | T | 3 | 1.5 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6
4 | Add new sprites (enemy) | T | 1 | 0.5 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 7
3 | Add new items | M | 2 | 2 | 0 |  | 2 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
1 | Add mini enemies & other challenges | S | 2 | 1.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
2 | Find and add music | T | 3 | 4 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10
3 | Add platforms to the levels | S | 2 | 1.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11
2 | Make the continuous level loop | M | 4 | 3.5 | 0 |  | 4 | 4 | 4 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12
2 | Effects when Pug eats item | S | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
2 | Make it look like Luna is walking | M | 2 | 2.25 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14
2 | Make it look like pug is walking | M | 2 | 1.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15
4 | Add backstory/instructions | T | 3 | 3 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
1 | Make it so Luna/the pug cannot go left | S | 1 | 0.25 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17
4 | Make Scores/timer look better | M | 2 | 0.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18
2 | Create the Basic Levels (themes/styles) | T | 1 | 0.5 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
3 | Add pause button | T | 2 | 1 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20
1 | Altering the movement of the bad guy when he falls behind | S | 1.5 | 1 | 0 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
2 | bad guy collision at start not working & platform issue | S | 1 | 0.5 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
1 | Make it game over if the player falls | M | 0.5 | 0.5 | 0 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
1 | Jumping problems (up arrow / too high) | S | 2 | 1.75 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24
1 | Make end spot for levels | S | 2 | 1.75 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25
2 | Make items/obstacles to make levels more difficult | M | 3 | 1 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26
2 | Make it look like the bad guy is walking | M | 2 | 1.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27
1 | Make a "You Won" scene/page thing | T | 0.5 | 0.5 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 35
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 37
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 38
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 39
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 41
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 43
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 44
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 46
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 47
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 49
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 51
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 52
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 53
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 55
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 56
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 57
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 58
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 59
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 61
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 62
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 64
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 66
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 67
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 68
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 69
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 70
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 71
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 73
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 74
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 77
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 78
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 79
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 81
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 82
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 83
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 85
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 86
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 87
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 88
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 89
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 90
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 91
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 92
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 93
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 94
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 95
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 97
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 98
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 99
[5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | 2017-11-17: Workdays |  | 101
| Shelby | S |  | Start Date | 2017-11-17 |  |  | 2017-11-17: Sun; 2017-11-20: 0; 2017-11-21: 0 |  | 102
| Tiffany | T |  | End Date | 2017-12-05 |  |  | 2017-11-17: Mon; 2017-11-20: 1; 2017-11-21: 1 |  | 103
| McKenna | M | [5 empty] | 2017-11-17: Tue; 2017-11-20: 1; 2017-11-21: 1 |  | 104
|  |  |  | Total Days | 18 |  |  | 2017-11-17: Wed; 2017-11-20: 1; 2017-11-21: 1 |  | 105
|  |  |  | Work Days | 12 |  |  | 2017-11-17: Thu; 2017-11-20: 1; 2017-11-21: 1 |  | 106
[8 empty] | 2017-11-17: Fri; 2017-11-20: 1; 2017-11-21: 3 |  | 107
| All | ALL | [5 empty] | 2017-11-17: Sat; 2017-11-20: 0; 2017-11-21: 0 |  | 108
| Unassigned | [25 empty] | 109
| Days to Look Back for Burndown Velocity | 2 | [24 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 12 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112
[6 empty] | On-Track Line | 45 | 45 | 41.25 | 37.5 | 33.75 | 30 | 26.25 | 22.5 | 18.75 | 15 | 11.25 | 7.5 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 113
114
[6 empty] | Sum | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 | 44.5 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 10 | 9.5 | 9 | 9 | 9 | 9 | 7.5 | 6.5 | 6 | 6 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 117
|  | 2 |  |  |  | Rank 2 | 23 | 23 | 23 | 23 | 22.5 | 22.5 | 22.5 | 21 | 16 | 16 | 12 | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 118
|  | 3 |  |  |  | Rank 3 | 6 | 6 | 5.5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 119
|  | 4 |  |  |  | Rank 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121
[6 empty] | Sum | 45 | 44.5 | 43.5 | 43 | 42.5 | 42.5 | 41 | 38.5 | 28 | 28 | 17 | 12 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 122
123
[6 empty] | Shelby | 14 | 14 | 13.5 | 13.5 | 13.5 | 13.5 | 12 | 11 | 9.5 | 9.5 | 5.5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 124
[6 empty] | Tiffany | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 12.5 | 8.5 | 8.5 | 3.5 | 3.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 125
[6 empty] | McKenna | 17.5 | 17 | 16.5 | 16 | 15.5 | 15.5 | 15.5 | 15 | 10 | 10 | 8 | 4.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 126
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 6 | [20 empty] | 136
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 |  | 137
[6 empty] | Average Assigned | 7.5 | 7.4167 | 7.25 | 7.1667 | 7.0833 | 7.0833 | 6.8333 | 6.4167 | 4.6667 | 4.6667 | 2.8333 | 2 | 0.58333 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138
[6 empty] | On-Track Line | 7.5 | 7.5 | 6.875 | 6.25 | 5.625 | 5 | 4.375 | 3.75 | 3.125 | 2.5 | 1.875 | 1.25 | 0.625 | 0 | 0 | 0 | 0 | 0 | 0 |  | 139
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 |  | 140
141
[7 empty] | 2017-11-16 | 2017-11-17 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-04 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 |  | 142
| Total Hours | 45 | [5 empty] | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 143
| Hours 2 Days Ago | 12 |  |  |  |  | 45 | 44.5 | 43.5 | 43 | 42.5 | 42.5 | 41 | 38.5 | 28 | 28 | 17 | 12 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144
| Hours Today | 0 |  |  |  | Burndown Velocity | 2017-12-01: 12; 2017-12-04: 6; 2017-12-05: 0; 2017-12-05: 0; 2017-12-05: 0; 2017-12-05: 0; 2017-12-05: 0; 2017-12-05: 0 |  | 145
| Today | 0 |  |  |  | BDV | 2017-11-16: 6 |  | 146
147
148
149
150
Note on B1: Please add "Team1" to the name of this document. -Matthew Evett

## Daily Scrum
2017-12-05 |  | Team Members
Dates |  | Shelby | Tiffany | McKenna | 0 | 0 | 0 | Workday
2017-11-17 | Fri | unable to work on project today. next: work on collider between pug and items (landing on items). help: none yet | Unable to work on project | Done: Made it so if the player falls off the ground, it goes to game over Next: Making the level continuous Help: Nothing yet |  |  |  | 1
2017-11-18 | Sat | [6 empty] | 0
2017-11-19 | Sun | [6 empty] | 0
2017-11-20 | Mon | done: editted pug collider to collect items even if the pug lands on the item next: make it so luna/the pug cannot go left help: none right now | Downloaded new backgrounds and sprites for new backguys Next: Put them all into their respective levels Help: Adding the background to the levels | Done: Added more items to be objects the pug can eat Next: Making the level continuous Help: Nothing yet |  |  |  | 1
2017-11-21 | Tue | Done: research on follow for bad buy Next:make Luna unable to go left Help: none yet | could not work on project today | Done: Worked more on adding objects that can be bad and good Next: Making the level more continuous Help: Nothing yet |  |  |  | 1
2017-11-22 | Wed | unable to work on project today next: make it so luna/the pug cannot go left help: none right now | could not work on project today | Done: Looked further into the continuous level Next: Getting the continuous level to make sense Help: Nothing |  |  |  | 1
2017-11-23 | Thu | unable to work on project today next: make it so luna/the pug cannot go left help: none right now | could not work on project today | Done: Unable to work on project today. Happy Thanksgiving! Next: Sprite animations Help: Nothing yet |  |  |  | 1
2017-11-24 | Fri | Done: made it so luna/pug cannot move left & worked on jump options Next: resolve jumping problems & bad guy movements Help: none yet | could not work on project today | Done: Worked on sprite animations for Luna Next: Finish sprite animations for Luna Help: What to do about the continuous level |  |  |  | 1
2017-11-25 | Sat | [6 empty] | 0
2017-11-26 | Sun | [6 empty] | 0
2017-11-27 | Mon | Done: worked on jumping/camera position problems Next: only allow user to jump when on ground or platform. Help: none right now | could not work on project today | Done: Added the rest of the objects for the pickup and made it so they are all spawned Next: Animations of Luna and Pug Help: Nothing yet |  |  |  | 1
2017-11-28 | Tue | Done: finalized jumping & fixed platforms spawning on ground. Next: animation Help: none right now | Done: First page of instructions, added related buttons Next: Continue instructions page and find music Help: troubleshooting why button doens't go to intro scene | Done: Added the rest of the objects for the pickup and made it so they are all spawned Next: Animations of Luna and Pug Help: Nothing yet |  |  |  | 1
2017-11-29 | Wed | unable to work on project today | Unable to work on project | Unable to work on project today |  |  |  | 1
2017-11-30 | Thu | Done: altered the bad guy collider so he won't collide when luna is on a platform & to fix start collision. added the different platforms to the different levels. extened the levels to an appropriate length to then add end point, fixed the grounds, finalized endpoints Next: effects when eating and bad guy movement Help: none needed | Finished working on backstory/instructions added pause and home buttons to each of the levels and continous mode Next: Find and add music Help: Need to seeing why some of the instruction buttons don't work | Done: Worked further on sprite animations Next: Finish animations Help: Nothing yet |  |  |  | 1
2017-12-01 | Fri | Done: altered bad guy movement so he won't fall between grounds & altered his movement so he won't fall too far behind luna Next: effects on pug eating & adding more challenges to the levels Help: none right now | Finished Added the music and fixed all the buttons Next: help where I can Help: none | Done: Finished sprite animations for Luna and Bad guy, found out how to make continuous level continuous Next: Finish continuous level Help: Nothing yet |  |  |  | 1
2017-12-02 | Sat | [6 empty] | 0
2017-12-03 | Sun | [6 empty] | 0
2017-12-04 | Mon | Done: worked on adding more obstacles and challenges to the levels. Added halos to items and obstacles Next: help where needed Help: none |  | Done: Finished continuous level Next: Work on bugs with continuous Help: Nothing yet |  |  |  | 1
2017-12-05 | Tue | Done: Changed the halos to other symbol for good verse bad items |  | Done: Fixed bugs with continuous mode Next: Sprint 3/Final Help: Nothing yet |  |  |  | 1
2017-12-06 | Wed | [6 empty] | 1
2017-12-07 | Thu | [6 empty] | 1
2017-12-08 | Fri | [6 empty] | 1